## Sheet1
SENG 300: Iteration 1
Colin A, Jessie C, Bryan H, Brandon L, Shaina R.
| Product Backlog |  |  | Sprint Backlog
ID | Story | Estimation | Priority | USER STORY | IN-PROGRESS | TO-DO | IN TESTING | DONE | DATE FINISHED | MEMBERS INVOLVED
1 | As a user, I wish to be able to register for an account with a username and password |  |  | As a user, I wish to be able to register for an account with a username and password | Done | Done | none | Create classes and attributes, architecture | 2019-02-20 | All
2 | As a user, I wish to be able to login to an existing account with a username and password | [6 empty] | Design front end layout for registration | 2019-02-25 | Jessie, Shaina
3 | As an authorized user, I wish to be able to view the list of available scholarships in the system | [6 empty] | Write code for database, registration | 2019-02-26 | Brandon, Bryan
4 | As an authorized user, I want to be able to view the general profile of a specified scholarship | [6 empty] | Test functionality for database, registration | 2019-02-26 | Brandon, Bryan
5 | As an authorized student, I want to be able to submit a scholarship application | [6 empty] | Code registration GUI and integrate with logic | 2019-02-27 | Shaina, Jessie
6 | As an authorized student, I want to be able to view all personal scholarship application submissions | [6 empty] | Verify and test resigtration GUI | 2019-02-27 | Shaina, Jessie
7 | As an authorized student, I want to be able to set a priority for scholarship applications | [7 empty] | 2019-02-27
8 | As an authorized student, I want to be able to resume an in-progress application form if not complete |  |  | As a user, I wish to be able to login to an existing account with a username and password | Done | Done | none | Write code for login page | 2019-02-27 | Shaina, Brandon
9 | As an administrator, I wish to be able to add new scholarships to the list of scholarships | [6 empty] | Test functionality of login with database | 2019-02-28 | Shaina, Brandon
10 | As an administrator, I wish to be able to remove existing scholarships
11 | As an administrator, I wish to be able to see all of the applicants for each respective scholarship | [6 empty] | Design front end layout for login | 2019-02-28 | Jessie, Shaina
12 | As an administrator, I wish to be able to add or edit a scholarships eligible requirements | [6 empty] | Code GUI for login | 2019-02-28 | Jessie, Shaina
13 | As an administrator, I wish to be able to filter student applications based on application eligibility | [6 empty] | Integrate login, registration, userdatabase classes with GUI | 2019-03-01 | Shaina, Brandon
14 | As an administrator, I wish to be able to process a scholarship application and grant or reject an application
15 | As an administrator, I wish to be able to filter the list of students based on specified criterias |  |  | As an authorized user, I wish to be able to view the list of available scholarships in the system | Code GUI for viewing scholarships in student | Code GUI for viewing scholarships in admin |  | Write code for scholarship, scholarship manager | 2019-02-27 | Colin
16 | As an authorized user, I wish to be able to view my user profile that contains all of my personal information |  |  |  | Linking Scholarship system to GUI |  |  | Write code for scholarshipApplication | 2019-02-27 | Colin
17 | As an authorized user, I wish to be able to receive notifications when there is an update to an application | [6 empty] | Design interface for viewing scholarships | 2019-03-03 | Shaina, Jessie
|  |  |  | As an authorized user, I want to be able to view the general profile of a specified scholarship | Linking Scholarship system to GUI | Grab scholarship data from the scholarship
Displaying data to the user interface
Iteration 1
ID | Story | Estimation | Priority
1 | As a user, I wish to be able to register for an account with a username and password | 2 | 1 | As an authorized student, I want to be able to submit a scholarship application | none | Search if the scholarship's data is available to view |  | Scholarship applications can be created and stored in database | 2019-02-27 | Colin
2 | As a user, I wish to be able to login to an existing account with a userID and password | 2 | 2 |  |  | Show the application required for the given scholarship
6 | As an authorized user, I wish to be able to view the list of available scholarships in the system | 3 | 3 |  |  | Take the scholarship application from the student and save it
9 | As an administrator, I wish to be able to add new scholarships to the list of scholarships | 4 | 4 |  |  | Add the scholarship application and save it to personal and scholarship database
10 | As an administrator, I wish to be able to remove existing scholarships | 6 | 5
12 | As an administrator, I wish to be able to add or edit a scholarships eligible requirements | 6 | 6 | As an authorized student, I want to be able to view all personal scholarship application submissions | none | Search personal data for any existing application
Display all existing scholarships in a list on the user interface
Ability to click each scholarship and view the student's own application
|  |  |  | As an authorized student, I want to be able to set a priority for scholarship applications | none | Search personal data for any existing scholarship applications
Display all scholarship applications
Be able to set priority with an apply button for each application in the list
|  |  |  | As an authorized student, I want to be able to resume an in-progress application form if not complete | none | Search for any open application
Pull data from database, refresh page with application
|  |  |  | As an administrator, I wish to be able to add new scholarships to the list of scholarships | none | Code a form to enter a new application with a set of criteria |  | Admin Gui Layout | 2019-02-28 | Jessie, Shaina
[6 empty] | Save the newly created application to the database |  | Scholarships can be created in database | 2019-02-27 | Colin
Refresh the list with the new scholarship
|  |  |  | As an administrator, I wish to be able to remove existing scholarships | none | Specify the scholarship to remove in a list |  | Scholarships can be removed from database | 2019-02-27 | Colin
If there are no applicants, delete the scholarship from the database
|  |  |  | As an administrator, I wish to be able to see all of the applicants for each respective scholarship | none | Specify a specific scholarship in a list |  | Students can be viewed | 2019-03-01 | Shaina, Brandon
Have a button to list all of the applicants for the scholarship specified
|  |  |  | As an administrator, I wish to be able to add or edit a scholarships eligible requirements | none | Specify a specific scholarship in a list
Have a dropdown and a button that will allow administrators to edit
Change fields as deeemed fit and store changes in the database
|  |  |  | As an administrator, I wish to be able to filter student applications based on application eligibility | none | Visually see the list of students that have applied for scholarships
Dropdown menus will refresh display to show filtered applications
|  |  |  | As an administrator, I wish to be able to process a scholarship application and grant or reject an application | none | Choose a specific scholarship application from the list
Check whether the scholarship application is eligible
Have a button that will process and grant the scholarship to the student
|  |  |  | As an administrator, I wish to be able to filter the list of students based on specified criterias | none | Display the list of all students in the system
Have a dropdown to specify filter type
Filter students based on student data such as faculty and year
|  |  |  | As an authorized user, I wish to be able to view my user profile that contains all of my personal information | none | Be able to click an icon in the corner of the application to open new scene |  | Profile Gui layout | 2019-02-28 | Jessie, Shaina
Scene pulls student data from the database
Display student data on the scene in organized format
|  |  |  | As an authorized user, I wish to be able to receive notifications when there is an update to an application | none | Display an icon in the user interface
Change the icon when there is an available notification
Remove notification after user has seen it